## Cost Plan
NHS Acute Hospital Wing — Elemental Cost Plan
Meridian Cost Consultants ¦ Report Date: 13 May 2026
Element Ref | Element Description | Budget (£) | Authorised Changes (£) | Revised Budget (£) | Committed (£) | Actual to Date (£) | Forecast Final Cost (£) | Variance (£) | % Complete
1.0 | Substructure | 800000 |  | 800000 | 800000 | 720000 | 805000 | -5000 | 100%
1.1 | Foundations | 540000 |  | 540000 | 540000 | 486000 | 540000 | 0 | 100%
1.2 | Basement & Ground Floor Slab | 260000 |  | 260000 | 260000 | 234000 | 265000 | -5000 | 100%
2.0 | Superstructure | 4290000 | 45000 | 4335000 | 4121000 | 3708950 | 4315000 | 20000 | 92.61%
2.1 | Frame & Upper Floors | 1800000 |  | 1800000 | 1800000 | 1620000 | 1800000 | 0 | 100%
2.2 | Roof | 650000 |  | 650000 | 650000 | 585000 | 650000 | 0 | 100%
2.3 | Staircases & Lifts | 280000 |  | 280000 | 266000 | 239400 | 272000 | 8000 | 95%
2.4 | External Walls & Windows | 950000 | 45000 | 995000 | 895500 | 806000 | 1045000 | -50000 | 85%
2.5 | Internal Walls & Partitions | 520000 |  | 520000 | 442000 | 397800 | 476000 | 44000 | 75%
2.6 | Internal Doors | 90000 |  | 90000 | 67500 | 60750 | 72000 | 18000 | 70%
3.0 | Internal Finishes | 790000 | 28000 | 818000 | 626500 | 501200 | 842000 | -24000 | 61.59%
3.1 | Wall Finishes | 380000 |  | 380000 | 304000 | 243200 | 391000 | -11000 | 65%
3.2 | Floor Finishes | 290000 | 28000 | 318000 | 238500 | 190800 | 325000 | -7000 | 60%
3.3 | Ceiling Finishes | 120000 |  | 120000 | 84000 | 67200 | 126000 | -6000 | 55%
4.0 | Fittings & Furnishings | 680000 |  | 680000 | 476000 | 380800 | 695000 | -15000 | 60%
5.0 | Services (MEP) | 7030000 | 157000 | 7187000 | 6752050 | 5403200 | 7484000 | -297000 | 66.27%
5.1 | Mechanical | 3240000 | 95000 | 3335000 | 3168250 | 2534600 | 3480000 | -145000 | 70%
5.2 | Electrical | 2340000 |  | 2340000 | 2223000 | 1780000 | 2456000 | -116000 | 65%
5.3 | Medical Gas & Specialist Services | 1450000 | 62000 | 1512000 | 1360800 | 1088600 | 1548000 | -36000 | 60%
6.0 | External Works | 600000 |  | 600000 | 360000 | 216000 | 628000 | -28000 | 45%
7.0 | Preliminaries | 2800000 | 85000 | 2885000 | 2885000 | 2596500 | 3100000 | -215000 | 65%
8.0 | Contingency | 1010000 |  | 1010000 | 0 | 0 | 850000 | 160000 | 0%
| Total Project Cost | 18000000 | 315000 | 18315000 | 16020550 | 13526650 | 18719000 | -404000 | 72.22%

## CVR
NHS Acute Hospital Wing — Cost Value Reconciliation
Meridian Cost Consultants ¦ Reporting Period: September 2024
Month | Cumulative Value (£) | Cumulative Cost (£) | Gross Margin (£) | Margin % | CPI | EAC
2024-04-01 | 850000 | 820000 | 30000 | 3.529% | 1.0366 | 17668588.2353
2024-05-01 | 1920000 | 1850000 | 70000 | 3.646% | 1.0378 | 17647265.625
2024-06-01 | 3450000 | 3350000 | 100000 | 2.899% | 1.0299 | 17784130.4348
2024-07-01 | 5280000 | 5180000 | 100000 | 1.894% | 1.0193 | 17968125
2024-08-01 | 8640000 | 8750000 | -110000 | -1.273% | 0.98743 | 18548177.0833
2024-09-01 | 11850000 | 12254650 | -404650 | -3.415% | 0.96698 | 18940414.7468
| 31990000 | 32204650

## Project Info
Project Name | NHS Acute Hospital Wing
Client | Manchester University NHS Foundation Trust
Contract Type | JCT Design and Build 2016
Project Value | 18000000
Start Date | 2024-04-01
Completion Date | 2026-03-31
Project Manager | Meridian Cost Consultants
Status | In Progress
% Complete | 0.65