## Cost Plan
Urban Highway Improvement Scheme — Elemental Cost Plan
Meridian Cost Consultants ¦ Report Date: 15 May 2026
Element Ref | Element Description | Budget (£) | Authorised Changes (£) | Revised Budget (£) | Committed (£) | Actual to Date (£) | Forecast Final Cost (£) | Variance (£) | % Complete
1.0 | Substructure | 1320000 | 0 | 1320000 | 1320000 | 880000 | 1320000 | 0 | 53.33%
1.1 | Foundations & Piling | 880000 |  | 880000 | 880000 | 660000 | 880000 | 0 | 60%
1.2 | Ground Floor Slab | 440000 |  | 440000 | 440000 | 220000 | 440000 | 0 | 40%
2.0 | Superstructure | 2860000 | 0 | 2860000 | 1320000 | 440000 | 2860000 | 0 | 13.85%
2.1 | Frame & Upper Floors | 1320000 |  | 1320000 | 1320000 | 440000 | 1320000 | 0 | 25%
2.2 | Roof & Weatherproofing | 660000 |  | 660000 | 0 | 0 | 660000 | 0 | 10%
2.3 | External Walls & Cladding | 880000 |  | 880000 | 0 | 0 | 880000 | 0 | 0%
3.0 | Internal Construction | 1100000 | 0 | 1100000 | 0 | 0 | 1100000 | 0 | 0%
3.1 | Internal Walls & Partitions | 440000 |  | 440000 | 0 | 0 | 440000 | 0 | 0%
3.2 | Raised Access Floors | 660000 |  | 660000 | 0 | 0 | 660000 | 0 | 0%
4.0 | Critical MEP Systems | 11220000 | 275000 | 11495000 | 4840000 | 968000 | 11770000 | -275000 | 6.551%
4.1 | High Voltage Power Infrastructure | 4840000 | 180000 | 5020000 | 4840000 | 968000 | 5200000 | -180000 | 15%
4.2 | Cooling & HVAC Systems | 3520000 |  | 3520000 | 0 | 0 | 3520000 | 0 | 0%
4.3 | Emergency Power & UPS | 1760000 | 95000 | 1855000 | 0 | 0 | 1950000 | -95000 | 0%
4.4 | Fire Suppression Systems | 1100000 |  | 1100000 | 0 | 0 | 1100000 | 0 | 0%
5.0 | External Works & Infrastructure | 1100000 | 0 | 1100000 | 0 | 0 | 1100000 | 0 | 0%
5.1 | Site Roads & Hardstanding | 660000 |  | 660000 | 0 | 0 | 660000 | 0 | 0%
5.2 | External Utilities Connections | 440000 |  | 440000 | 0 | 0 | 440000 | 0 | 0%
6.0 | Security & Access Control | 880000 |  | 880000 | 0 | 0 | 880000 | 0 | 0%
7.0 | Preliminaries | 2640000 | 45000 | 2685000 | 2685000 | 537000 | 2800000 | -115000 | 20%
8.0 | Contingency | 880000 |  | 880000 | 0 | 0 | 680000 | 200000 | 0%
| Total Project Cost | 22000000 | 320000 | 22320000 | 10165000 | 2825000 | 22510000 | -190000 | 10.79%

## CVR
Data Centre Shell & Core — Cost Value Reconciliation
Meridian Cost Consultants ¦ Reporting Period: March 2026
Month | Cumulative Value (£) | Cumulative Cost (£) | Gross Margin (£) | Margin % | CPI | EAC
2026-02-01 | 1200000 | 1350000 | -150000 | -12.5% | 0.88889 | 25110000
2026-03-01 | 2650000 | 2825000 | -70000 | -7.143% | 0.93333 | 23914285.7143
| 3850000 | 4175000

## Project Info
Project Name | Urban Highway Improvement Scheme
Client | Transport for Greater Manchester
Contract Type | NEC4 Engineering and Construction Contract
Project Value | 32000000
Start Date | 2023-09-01
Completion Date | 2026-02-28
Project Manager | Meridian Cost Consultants
Status | In Progress
% Complete | 10.79%