## Cost Plan
Government Office Refurbishment — Elemental Cost Plan
Meridian Cost Consultants ¦ Report Date: 15 May 2026
Element Ref | Element Description | Budget (£) | Authorised Changes (£) | Revised Budget (£) | Committed (£) | Actual to Date (£) | Forecast Final Cost (£) | Variance (£) | % Complete
1.0 | Strip Out & Demolition | 525000 | 0 | 525000 | 525000 | 505000 | 545000 | -20000 | 100%
1.1 | Soft Strip Out | 225000 |  | 225000 | 225000 | 225000 | 225000 | 0 | 100%
1.2 | Structural Alterations | 300000 |  | 300000 | 300000 | 280000 | 320000 | -20000 | 100%
2.0 | Fabric Repairs & Renewals | 1050000 | 45000 | 1095000 | 1095000 | 990000 | 1120000 | -25000 | 95.48%
2.1 | Roof Repairs & Renewals | 375000 |  | 375000 | 375000 | 375000 | 375000 | 0 | 100%
2.2 | Facade & Window Replacements | 450000 |  | 450000 | 450000 | 405000 | 465000 | -15000 | 95%
2.3 | Internal Structural Repairs | 225000 | 45000 | 270000 | 270000 | 210000 | 280000 | -10000 | 90%
3.0 | Internal Fit Out | 1275000 | 0 | 1275000 | 1031250 | 742500 | 1290000 | -15000 | 53.53%
3.1 | Partitioning & Internal Doors | 450000 |  | 450000 | 382500 | 270000 | 450000 | 0 | 55%
3.2 | Wall, Floor & Ceiling Finishes | 600000 |  | 600000 | 480000 | 360000 | 615000 | -15000 | 50%
3.3 | Joinery & Ironmongery | 225000 |  | 225000 | 168750 | 112500 | 225000 | 0 | 60%
4.0 | Fittings & Furnishings | 525000 | 0 | 525000 | 292500 | 146250 | 525000 | 0 | 37.86%
4.1 | Fixed Furniture & Storage | 300000 |  | 300000 | 180000 | 90000 | 300000 | 0 | 40%
4.2 | Loose Furniture & Equipment | 225000 |  | 225000 | 112500 | 56250 | 225000 | 0 | 35%
5.0 | Building Services | 2700000 | 100000 | 2800000 | 2583500 | 1872000 | 2825000 | -25000 | 61.48%
5.1 | Mechanical & HVAC | 1350000 | 68000 | 1418000 | 1282500 | 945000 | 1420000 | -2000 | 50%
5.2 | Electrical & Data | 1050000 | 32000 | 1082000 | 1016000 | 756000 | 1095000 | -13000 | 70%
5.3 | Lift Refurbishment | 300000 |  | 300000 | 285000 | 171000 | 310000 | -10000 | 85%
6.0 | External Works & Landscaping | 225000 |  | 225000 | 112500 | 0 | 225000 | 0 | 10%
7.0 | Preliminaries | 900000 | 55000 | 955000 | 955000 | 637500 | 980000 | -25000 | 60%
8.0 | Contingency | 300000 |  | 300000 | 0 | 0 | 250000 | 50000 | 0%
| Total Project Cost | 7500000 | 200000 | 7700000 | 6594750 | 4893250 | 7760000 | -60000 | 64.24%

## CVR
Government Office Refurbishment — Cost Value Reconciliation
Meridian Cost Consultants ¦ Reporting Period: March 2026
Month | Cumulative Value (£) | Cumulative Cost (£) | Gross Margin (£) | Margin % | CPI | EAC
2025-07-01 | 920000 | 980000 | -60000 | -6.522% | 0.93878 | 8202173.913
2025-08-01 | 1680000 | 1780000 | -100000 | -5.952% | 0.94382 | 8158333.3333
2025-09-01 | 2450000 | 2590000 | -140000 | -5.714% | 0.94595 | 8140000
2025-10-01 | 3280000 | 3450000 | -170000 | -5.183% | 0.95072 | 8099085.3659
2025-11-01 | 4100000 | 4280000 | -180000 | -4.39% | 0.95794 | 8038048.7805
2025-12-01 | 4850000 | 5050000 | -200000 | -4.124% | 0.9604 | 8017525.7732
2026-01-01 | 5520000 | 5740000 | -220000 | -3.986% | 0.96167 | 8006884.058
2026-02-01 | 6180000 | 6420000 | -240000 | -3.883% | 0.96262 | 7999029.1262
2026-03-01 | 6720000 | 6980000 | -260000 | -3.869% | 0.96275 | 7997916.6667
| 35700000 | 37270000

## Project Info
Project Name | Government Office Refurbishment
Client | His Majesty's Revenue & Customs
Contract Type | JCT Intermediate Building Contract 2016
Project Value | 7500000
Start Date | 2024-03-01
Completion Date | 2025-02-28
Project Manager | Meridian Cost Consultants
Status | In Progress
% Complete | 64.24%