## Cost Plan
Primary School Expansion — Elemental Cost Plan
Meridian Cost Consultants ¦ Report Date: 16 May 2026
Element Ref | Element Description | Budget (£) | Authorised Changes (£) | Revised Budget (£) | Committed (£) | Actual to Date (£) | Forecast Final Cost (£) | Variance (£) | % Complete
1.0 | Substructure | 294000 | 0 | 294000 | 294000 | 294000 | 294000 | 0 | 100%
1.1 | Foundations | 168000 |  | 168000 | 168000 | 168000 | 168000 | 0 | 100%
1.2 | Ground Floor Slab | 126000 |  | 126000 | 126000 | 126000 | 126000 | 0 | 100%
2.0 | Superstructure | 1092000 | 28000 | 1120000 | 1120000 | 1120000 | 1120000 | 0 | 100%
2.1 | Frame & Upper Floors | 378000 |  | 378000 | 378000 | 378000 | 378000 | 0 | 100%
2.2 | Roof | 252000 |  | 252000 | 252000 | 252000 | 252000 | 0 | 100%
2.3 | External Walls & Windows | 294000 | 28000 | 322000 | 322000 | 322000 | 322000 | 0 | 100%
2.4 | Internal Walls & Doors | 168000 |  | 168000 | 168000 | 168000 | 168000 | 0 | 100%
3.0 | Internal Finishes | 504000 | 0 | 504000 | 504000 | 504000 | 504000 | 0 | 100%
3.1 | Wall Finishes | 168000 |  | 168000 | 168000 | 168000 | 168000 | 0 | 100%
3.2 | Floor Finishes | 210000 |  | 210000 | 210000 | 210000 | 210000 | 0 | 100%
3.3 | Ceiling Finishes | 126000 |  | 126000 | 126000 | 126000 | 126000 | 0 | 100%
4.0 | Fittings & Furnishings | 210000 |  | 210000 | 210000 | 210000 | 210000 | 0 | 100%
5.0 | Building Services | 798000 | 18000 | 816000 | 816000 | 816000 | 816000 | 0 | 100%
5.1 | Mechanical & HVAC | 462000 |  | 462000 | 462000 | 462000 | 462000 | 0 | 100%
5.2 | Electrical & Lighting | 336000 | 18000 | 354000 | 354000 | 354000 | 354000 | 0 | 100%
6.0 | External Works & Playground | 252000 | 32000 | 284000 | 284000 | 284000 | 284000 | 0 | 100%
7.0 | Preliminaries | 882000 |  | 882000 | 882000 | 882000 | 882000 | 0 | 100%
8.0 | Contingency | 168000 |  | 168000 | 0 | 0 | 0 | 168000 | 0%
| Total Project Cost | 4200000 | 78000 | 4278000 | 4110000 | 4110000 | 4110000 | 168000 | 100%

## CVR
Primary School Expansion — Cost Value Reconciliation
Meridian Cost Consultants ¦ Reporting Period: March 2026
Month | Cumulative Value (£) | Cumulative Cost (£) | Gross Margin (£) | Margin % | CPI | EAC
2025-09-01 | 620000 | 590000 | 30000 | 4.839% | 1.0508 | 4071000
2025-10-01 | 1250000 | 1190000 | 60000 | 4.8% | 1.0504 | 4072656
2025-11-01 | 1980000 | 1880000 | 100000 | 5.051% | 1.0532 | 4061939.3939
2025-12-01 | 2720000 | 2580000 | 140000 | 5.147% | 1.0543 | 4057808.8235
2026-01-01 | 3380000 | 3210000 | 170000 | 5.03% | 1.053 | 4062834.3195
2026-02-01 | 3850000 | 3660000 | 190000 | 4.935% | 1.0519 | 4066877.9221
2026-03-01 | 4110000 | 4110000 | 0 | 0% | 1 | 4278000
| 17910000 | 17220000

## Project Info
Project Name | Primary School Expansion
Client | Cheshire West and Chester Council
Contract Type | JCT Intermediate Building Contract 2016
Project Value | 4200000
Start Date | 2024-09-01
Completion Date | 2025-08-31
Project Manager | Meridian Cost Consultants
Status | Complete
% Complete | 100%
Sector | Education