## Cost Plan
Urban Highway Improvement Scheme — Elemental Cost Plan
Meridian Cost Consultants ¦ Report Date: 16 May 2026
Element Ref | Element Description | Budget (£) | Authorised Changes (£) | Revised Budget (£) | Committed (£) | Actual to Date (£) | Forecast Final Cost (£) | Variance (£) | % Complete
1.0 | Demolition & Site Clearance | 1280000 | 180000 | 1460000 | 1440000 | 1340000 | 1580000 | -120000 | 94.86%
1.1 | Demolition of Existing Structures | 640000 |  | 640000 | 640000 | 640000 | 640000 | 0 | 100%
1.2 | Site Clearance & Stripping | 320000 |  | 320000 | 320000 | 320000 | 320000 | 0 | 100%
1.3 | Contamination Remediation | 320000 | 180000 | 500000 | 480000 | 380000 | 620000 | -120000 | 85%
2.0 | Earthworks | 6400000 | 95000 | 6495000 | 5695000 | 4560000 | 7100000 | -605000 | 66.87%
2.1 | Bulk Excavation & Filling | 3200000 | 95000 | 3295000 | 3295000 | 2640000 | 3580000 | -285000 | 75%
2.2 | Embankments & Cuttings | 2240000 |  | 2240000 | 1680000 | 1344000 | 2420000 | -180000 | 60%
2.3 | Temporary Works & Support | 960000 |  | 960000 | 720000 | 576000 | 1100000 | -140000 | 55%
3.0 | Pavements | 5760000 | 0 | 5760000 | 3328000 | 1664000 | 5760000 | 0 | 28.89%
3.1 | Carriageway Construction | 4480000 |  | 4480000 | 2688000 | 1344000 | 4480000 | 0 | 30%
3.2 | Footways & Cycleways | 1280000 |  | 1280000 | 640000 | 320000 | 1280000 | 0 | 25%
4.0 | Structures | 7040000 | 220000 | 7260000 | 5664000 | 3648000 | 7650000 | -390000 | 47.95%
4.1 | Bridges & Culverts | 4800000 | 220000 | 5020000 | 4320000 | 2880000 | 5200000 | -180000 | 55%
4.2 | Retaining Walls | 1600000 |  | 1600000 | 960000 | 576000 | 1750000 | -150000 | 35%
4.3 | Drainage Structures | 640000 |  | 640000 | 384000 | 192000 | 700000 | -60000 | 25%
5.0 | Highway Services & Lighting | 2560000 | 0 | 2560000 | 928000 | 464000 | 2560000 | 0 | 18.12%
5.1 | Street Lighting | 1600000 |  | 1600000 | 640000 | 320000 | 1600000 | 0 | 20%
5.2 | Traffic Signals & ITS | 960000 |  | 960000 | 288000 | 144000 | 960000 | 0 | 15%
6.0 | Landscaping & Ecology | 960000 |  | 960000 | 192000 | 0 | 960000 | 0 | 0%
7.0 | Preliminaries | 5760000 | 145000 | 5905000 | 5905000 | 2962500 | 6200000 | -295000 | 45%
8.0 | Contingency | 2240000 |  | 2240000 | 0 | 0 | 1800000 | 440000 | 0%
| Total Project Cost | 32000000 | 640000 | 32640000 | 23152000 | 14638500 | 33610000 | -970000 | 45.09%

## CVR
Urban Highway Improvement Scheme — Cost Value Reconciliation
Meridian Cost Consultants ¦ Reporting Period: September 2024
Month | Cumulative Value (£) | Cumulative Cost (£) | Gross Margin (£) | Margin % | CPI | EAC
2023-09-01 | 480000 | 510000 | -30000 | -6.25% | 0.94118 | 34680000
2023-10-01 | 980000 | 1050000 | -70000 | -7.143% | 0.93333 | 34971428.5714
2023-11-01 | 1650000 | 1780000 | -130000 | -7.879% | 0.92697 | 35211636.3636
2023-12-01 | 2100000 | 2280000 | -180000 | -8.571% | 0.92105 | 35437714.2857
2024-01-01 | 2820000 | 3050000 | -230000 | -8.156% | 0.92459 | 35302127.6596
2024-02-01 | 3680000 | 3980000 | -300000 | -8.152% | 0.92462 | 35300869.5652
2024-03-01 | 4950000 | 5280000 | -330000 | -6.667% | 0.9375 | 34816000
2024-04-01 | 6240000 | 6620000 | -380000 | -6.09% | 0.9426 | 34627692.3077
2024-05-01 | 7680000 | 8100000 | -420000 | -5.469% | 0.94815 | 34425000
2024-06-01 | 9120000 | 9650000 | -530000 | -5.811% | 0.94508 | 34536842.1053
2024-07-01 | 10560000 | 11150000 | -590000 | -5.587% | 0.94709 | 34463636.3636
2024-08-01 | 11800000 | 12450000 | -650000 | -5.508% | 0.94779 | 34437966.1017
2024-09-01 | 12950000 | 13650000 | -700000 | -5.405% | 0.94872 | 34404324.3243
2024-10-01 | 13920000 | 14650000 | -730000 | -5.244% | 0.95017 | 34351724.1379
2024-11-01 | 14650000 | 15420000 | -770000 | -5.256% | 0.95006 | 34355549.4881
2024-12-01 | 15280000 | 16080000 | -800000 | -5.236% | 0.95025 | 34348900.5236
2025-01-01 | 15820000 | 16650000 | -830000 | -5.247% | 0.95015 | 34352465.2339
2025-02-01 | 16250000 | 17100000 | -850000 | -5.231% | 0.95029 | 34347323.0769
2025-03-01 | 16640000 | 17610000 | -970000 | -5.829% | 0.94492 | 34542692.3077
| 167570000 | 177060000

## Project Info
Project Name | Urban Highway Improvement Scheme
Client | Transport for Greater Manchester
Contract Type | NEC4 Engineering and Construction Contract
Project Value | 32000000
Start Date | 2023-09-01
Completion Date | 2026-02-28
Project Manager | Meridian Cost Consultants
Status | In Progress
% Complete | 45.09%
Sector | Infrastructure